## Sheet1
Date | Update
Till 03/13/25 | Proposal, Arch and Micro Arch review
2025-03-18 | Finished initial implementation of BRAM controller and tested it. It has 8, 256 bit vector registers and two line buffers. Also have a psudo implementation of SDRAM controller based on Minilab 2. Needs more verification
2025-03-31 | Was able to use and access the FPGA sdram controller. Seemed to work fine when tested manually but still some inconsistencies when accessing sequentially. Tried to implement the axi bridge and access HPS sdram but having few issues. Need to discuss with team and TA/instructor.
2025-04-13 | Created a qsys setup with hps and dma controllers but seemed like accessing the hps using Linux was not a viable option. So, changed plan to use the FPGA Sdram instead and use JTAG master to load up memory from external pc. Also creadted a custom IP named SDRAM_Wrapper and connected in QSYS that can be used in other modules to rd/wr from sdram. So, Memory part of the project is done, just need to integrated with design.