## Sheet1
Date | Update
Till 03/13/25 | Proposal, Arch and Micro Arch review
2025-03-18 | Finished initial implementation of BRAM controller and tested it. It has 8, 256 bit vector registers and two line buffers. Also have a psudo implementation of SDRAM controller based on Minilab 2. Needs more verification
2025-03-31 | Was able to use and access the FPGA sdram controller. Seemed to work fine when tested manually but still some inconsistencies when accessing sequentially. Tried to implement the axi bridge and access HPS sdram but having few issues. Need to discuss with team and TA/instructor.